## Issues&New Exceptions
Sl No. | Reported Date | Issues | Newly developed/handled by BOT | Resolved/Alternate Solution | Cases(As Example) | Efforts in Days | CR/Additional Exception ?
1 | 2019-09-02 | Buisness Partner Email ID/ Buyer email ID blank/incorrect | NA | No | 2000485254/H5041600560 | 1 | No
2 | 2019-09-02 | Invoice Categorization not done properly | 1. If Doc Type=Service and Ivoice Category= Material Supply moving to manual. 2. If CHA comes as SEZ/Material Supply moving to manual. 3. If SEZ comes as Material Supply, the flow will go as Material Supply only so we have kept a validation to check whether its a SEZ plant in the code so that we can replace with 00 tax code if neccessary. | It is not resolved but BOT following alternate solution moving to Manual Q except SEZ comes as Material Supply. | H5041624489(CHA but came as SEZ) | 1 | No
3 | 2019-09-02 | Service Entry Number incorrect or dummy value | Moving to genpact if SE no. is available with incorrect data | BOT following alternate solution moving to Manual Q | H5041679009 | 1 | No
5 | 2019-09-03 | Related Party Vendors | If BOT encounters Related Party vendor cases we are typing 'Yes' in the corncerned TextBox and moving to genpact | BOT following alternate solution moving to Manual Q |  | 1 | No
6 | 2019-09-03 | Fasttrack cases are coming to BOT | BOT is moving these cases to manual. | BOT following alternate solution moving to Manual Q |  | 1 | No
7 | 2019-09-03 | Tax Code from Excel | Earlier it was informed the categories will be C for Company and P for Individual later it was confirmed that P or H is to be considered for Non Company | Resolved by RPA |  | 1 | CR/Additional Exception
8 | 2019-09-03 | Transport Cases | 1. As informed earlier, We encountered many new scenarios which were neither informed to us nor we got such scenarios in UAT | No |  | 5 | CR/Additional Exception
| 2019-09-03 | b. GRN not captured for Transport as it is mandatory | Moving to genpact if GRN not captured in CM |  |  |  | CR/Additional Exception
10 | 2019-09-04 | New Scenario: For some Service Invoices, after entering the SE no. either the PO line items are not coming or Amount and Quantity is blank which makes the BOT stop | Yet to be developed after NON PO completion | No |  | 1.5 | CR/Additional Exception
11 | 2019-09-05 | For already processing fine cases we encountered new pop up for Baseline date | We already handled it previously, but again this pop up is coming sometime unexpectedly, which is now handled. | Resolved by RPA |  | 1 | CR/Additional Exception
12 | 2019-09-06 | a. Coal Cases: Since Hardcopy DC No. is important to be captured in CM if the line item is not matching with the reference no. | Moving to genpact | BOT following alternate solution moving to Manual Q |  | 1 | No
| 2019-09-06 | b. Received wrong Quatity from CM(since BOT will only rely on input from CM; if such case comes, the BOT will proceed with Quantity mismatch scenario and hence the calculations will be acc. To what we have recievd ) | Resolution yet to be provided by corncerned | No |  | 2 | No
13 | 2019-09-06 | While processing in SAP we encountered new error message "You cannot post to this(asset 13004784) Blocked for acquisation" | Yet to be developed after NON PO completion | No | 2000489164 | 1 | No
14 | 2019-09-11 | Service | Cases with no line item in PO | Yes |  | 2.5 | CR/Additional Exception
Cases with blank Amount and blank Quantity
Get the Tax Code from PO History
15 | 2019-09-11 | Simulate | We are validating IGST/ SGST in Simulate Screen but earlier Ram asked not to take any action if any mismatch, but now Ayyappa is asking to validate and if mismatch in IGST or CGST/SGST send to manual Q | No |  | 1 | CR/Additional Exception
16 | 2019-09-12 | New Pop up | PO document not yet released(encountered today) | No |  | 1.5 | CR/Additional Exception
|  |  | Baseline Date Pop ups are coming sometimes unexpectedly | No |  |  | CR/Additional Exception
17 | 2019-09-13 | Credit Note | Need to move to genpact | No |  | 1 | CR/Additional Exception
18 | 2019-09-13 | Fasttrack | Need to move to genpact/ handled already but it is not fixed which field will be updated as Fasttrack, so we have to keep check for 3 fields which may contain 'Fasttrack' | No |  | 1 | No
19 | 2019-09-11 | Non-Po | Handling Both Screens for all scenarios | Yes |  | 2 | CR/Additional Exception